## Sheet1
Date | Week | Coding Progress | Technical Report Progress | PowerPoint Progress | Team member | Work Comment
2024-10-03 | Week 1 | Not Started | Not Started | Not Started
2024-10-04 | Week 1 | Not Started | Not Started | Not Started
2024-10-05 | Week 1 | Not Started | Not Started | Not Started
2024-10-06 | Week 1 | Not Started | Not Started | Not Started
2024-10-07 | Week 1 | Not Started | Not Started | Not Started
2024-10-08 | Week 1 | Not Started | Not Started | Not Started
2024-10-09 | Week 1 | Not Started | Not Started | Not Started
2024-10-10 | Week 2 | Not Started | Not Started | Not Started
2024-10-11 | Week 2 | Not Started | Not Started | Not Started
2024-10-12 | Week 2 | Not Started | Not Started | Not Started
2024-10-13 | Week 2 | Not Started | Not Started | Not Started
2024-10-14 | Week 2 | Not Started | Not Started | Not Started | Ayman | Iteration #02 Submission
2024-10-15 | Week 2 | Not Started | Not Started | Not Started
2024-10-16 | Week 2 | Not Started | Not Started | Not Started
2024-10-17 | Week 3 | In Progress | Not Started | Not Started | Ayman, Amisha, Ronhit | Project Idea discussion
2024-10-18 | Week 3 | In Progress | Not Started | Not Started | Ayman, Amisha, Ronhit | Dataset choice
2024-10-19 | Week 3 | In Progress | Not Started | Not Started | Ayman, Amisha, Ronhit | Dataset finalised
2024-10-20 | Week 3 | In Progress | Not Started | Not Started
2024-10-21 | Week 3 | In Progress | Not Started | Not Started | Ayman | Git Hub initial Repo Setup Complete
2024-10-22 | Week 3 | In Progress | Not Started | Not Started
2024-10-23 | Week 3 | In Progress | In Progress | Not Started
2024-10-24 | Week 4 | In Progress | In Progress | Not Started | Ayman, Amisha, Ronhit | Discussion on Preprocessing and Model
2024-10-25 | Week 4 | In Progress | In Progress | Not Started | Ayman, Amisha, Ronhit | EDA discussion
2024-10-26 | Week 4 | In Progress | In Progress | Not Started | Ayman, Amisha, Ronhit | Tasks vaguely discussed and assigned
2024-10-27 | Week 4 | In Progress | In Progress | Not Started
2024-10-28 | Week 4 | In Progress | In Progress | Not Started
2024-10-29 | Week 4 | In Progress | In Progress | Not Started | Ayman, Amisha, Ronhit | Data Set loaded
2024-10-30 | Week 4 | In Progress | In Progress | Not Started
2024-10-31 | Week 5 | In Progress | In Progress | Not Started | Ayman | Dataset loaded in code
2024-11-01 | Week 5 | In Progress | In Progress | Not Started | Ronhit | Started EDA
2024-11-02 | Week 5 | In Progress | In Progress | Not Started
2024-11-03 | Week 5 | In Progress | In Progress | Not Started | Ronhit | Initial EDA complete
2024-11-04 | Week 5 | In Progress | In Progress | Not Started | Amisha | started visualization
2024-11-05 | Week 5 | In Progress | In Progress | Not Started | Ayman | Started data cleanning
2024-11-06 | Week 5 | In Progress | In Progress | Not Started
2024-11-07 | Week 6 | In Progress | In Progress | Not Started | Ayman, Amisha, Ronhit | Discussion on progress and requirements for Iteration3 as discussed in class
2024-11-08 | Week 6 | In Progress | In Progress | Not Started | Ayman | Completed Data cleaning and Preprocessing
2024-11-09 | Week 6 | In Progress | In Progress | Not Started | Amisha | Added column to clean dataset and visualizations
2024-11-10 | Week 6 | In Progress | In Progress | Not Started | Ayman, Amisha, Ronhit | checked in all code to git based on assigned issues and worked on Iteration3 report and submission
2024-11-11 | Week 6 | Not Started | Not Started | Not Started
2024-11-12 | Week 6 | Not Started | Not Started | Not Started
2024-11-13 | Week 6 | Not Started | Not Started | Not Started
2024-11-14 | Week 7 | Not Started | Not Started | Not Started
2024-11-15 | Week 7 | Not Started | Not Started | Not Started
2024-11-16 | Week 7 | Not Started | Not Started | Not Started
2024-11-17 | Week 7 | Not Started | Not Started | Not Started
2024-11-18 | Week 7 | Not Started | Not Started | Not Started
2024-11-19 | Week 7 | Not Started | Not Started | Not Started
2024-11-20 | Week 7 | Not Started | Not Started | Not Started
2024-11-21 | Week 8 | Not Started | Not Started | Not Started
2024-11-22 | Week 8 | Not Started | Not Started | Not Started
2024-11-23 | Week 8 | Not Started | Not Started | Not Started
2024-11-24 | Week 8 | Not Started | Not Started | Not Started
2024-11-25 | Week 8 | Not Started | Not Started | Not Started
2024-11-26 | Week 8 | Not Started | Not Started | Not Started
2024-11-27 | Week 8 | Not Started | Not Started | Not Started
2024-11-28 | Week 9 | Not Started | Not Started | Not Started